## Activities
Activity ID | WBS ID | Activity Code | Activity Name | Activity Type | Original Duration (days) | Remaining Duration (days) | % Complete | Status | Actual Start | Actual Finish | Early Start | Early Finish | Late Start | Late Finish | Total Float (days) | Critical
MS200 | ALEXTWR-WBS01 | MS200 | Notice to Proceed | Milestone | 0 | 0 | 100 | Complete | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 0 | Y
B1010 | ALEXTWR-WBS01 | B1010 | Excavation & Piling | Task | 25 | 0 | 100 | Complete | 2026-03-01 | 2026-03-26 | 2026-03-01 | 2026-03-26 | 2026-03-01 | 2026-03-26 | 0 | Y
B1020 | ALEXTWR-WBS01 | B1020 | Foundation & Raft | Task | 20 | 0 | 100 | Complete | 2026-03-26 | 2026-04-15 | 2026-03-26 | 2026-04-15 | 2026-03-26 | 2026-04-15 | 0 | Y
B1030 | ALEXTWR-WBS01 | B1030 | Ground Floor Structure | Task | 20 | 0 | 100 | Complete | 2026-04-15 | 2026-05-05 | 2026-04-15 | 2026-05-05 | 2026-04-15 | 2026-05-05 | 0 | Y
B1040 | ALEXTWR-WBS01 | B1040 | Typical Floor Structure (1F-5F) | Task | 40 | 0 | 100 | Complete | 2026-05-05 | 2026-06-14 | 2026-05-05 | 2026-06-14 | 2026-05-05 | 2026-06-14 | 0 | Y
B1050 | ALEXTWR-WBS01 | B1050 | MEP Rough-in | Task | 30 | 0 | 100 | Complete | 2026-06-14 | 2026-07-14 | 2026-06-14 | 2026-07-14 | 2026-06-14 | 2026-07-14 | 0 | Y
B1060 | ALEXTWR-WBS01 | B1060 | Finishes | Task | 35 | 2 | 94 | In Progress | 2026-07-14 |  | 2026-07-14 | 2026-08-18 | 2026-07-14 | 2026-08-18 | 0 | Y
MS210 | ALEXTWR-WBS01 | MS210 | Practical Completion / Handover | Milestone | 0 | 0 | 0 | Not Started |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 0 | Y