## WBS
WBS ID | Parent WBS ID | WBS Code | WBS Name
WBS001 |  | 1.0 | New HQ Building - Cairo
WBS002 | WBS001 | 1.1 | Preliminaries & Mobilization
WBS003 | WBS001 | 1.2 | Substructure
WBS004 | WBS001 | 1.3 | Superstructure
WBS005 | WBS001 | 1.4 | MEP Installation
WBS006 | WBS001 | 1.5 | Finishes
WBS007 | WBS001 | 1.6 | External Works & Handover

## Activities
Activity ID | WBS ID | Activity Code | Activity Name | Activity Type | Original Duration (days) | Remaining Duration (days) | % Complete | Status | Actual Start | Actual Finish | Early Start | Early Finish | Late Start | Late Finish | Total Float (days) | Critical
MS100 | WBS002 | MS100 | Notice to Proceed | Milestone | 0 | 0 | 100 | Complete | 01-Feb-2026 | 01-Feb-2026 | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | 0 | Y
A1010 | WBS002 | A1010 | Mobilize Site & Setup Facilities | Task | 10 | 0 | 100 | Complete | 01-Feb-2026 | 11-Feb-2026 | 2026-02-01 | 2026-02-11 | 2026-02-01 | 2026-02-11 | 0 | Y
A1020 | WBS002 | A1020 | Site Survey & Setting Out | Task | 7 | 0 | 100 | Complete | 11-Feb-2026 | 18-Feb-2026 | 2026-02-11 | 2026-02-18 | 2026-02-11 | 2026-02-18 | 0 | Y
A1030 | WBS003 | A1030 | Excavation & Earthworks | Task | 20 | 0 | 100 | Complete | 18-Feb-2026 | 10-Mar-2026 | 2026-02-18 | 2026-03-10 | 2026-02-18 | 2026-03-10 | 0 | Y
A1040 | WBS003 | A1040 | Piling Works | Task | 25 | 0 | 100 | Complete | 10-Mar-2026 | 04-Apr-2026 | 2026-03-10 | 2026-04-04 | 2026-03-10 | 2026-04-04 | 0 | Y
A1050 | WBS003 | A1050 | Pile Caps & Foundations | Task | 18 | 0 | 100 | Complete | 04-Apr-2026 | 22-Apr-2026 | 2026-04-04 | 2026-04-22 | 2026-04-04 | 2026-04-22 | 0 | Y
A1060 | WBS003 | A1060 | Basement Retaining Walls | Task | 20 | 0 | 100 | Complete | 22-Apr-2026 | 12-May-2026 | 2026-04-22 | 2026-05-12 | 2026-04-22 | 2026-05-12 | 0 | Y
MS110 | WBS003 | MS110 | Substructure Complete | Milestone | 0 | 0 | 100 | Complete | 12-May-2026 | 12-May-2026 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 0 | Y
A1070 | WBS004 | A1070 | Ground Floor Columns & Slab | Task | 18 | 0 | 100 | Complete | 12-May-2026 | 30-May-2026 | 2026-05-12 | 2026-05-30 | 2026-05-12 | 2026-05-30 | 0 | Y
A1080 | WBS004 | A1080 | 1st Floor Columns & Slab | Task | 18 | 0 | 100 | Complete | 30-May-2026 | 17-Jun-2026 | 2026-05-30 | 2026-06-17 | 2026-05-30 | 2026-06-17 | 0 | Y
A1090 | WBS004 | A1090 | 2nd Floor Columns & Slab | Task | 18 | 0 | 100 | Complete | 17-Jun-2026 | 05-Jul-2026 | 2026-06-17 | 2026-07-05 | 2026-06-17 | 2026-07-05 | 0 | Y
A1100 | WBS004 | A1100 | Roof Slab & Structure | Task | 15 | 0 | 100 | Complete | 05-Jul-2026 | 20-Jul-2026 | 2026-07-05 | 2026-07-20 | 2026-07-05 | 2026-07-20 | 0 | Y
MS120 | WBS004 | MS120 | Structure Topping Out | Milestone | 0 | 0 | 100 | Complete | 20-Jul-2026 | 20-Jul-2026 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 0 | Y
A1110 | WBS005 | A1110 | Electrical First Fix | Task | 25 | 1 | 96 | In Progress | 23-Jul-2026 |  | 2026-07-23 | 2026-08-17 | 2026-07-23 | 2026-08-17 | 0 | Y
A1120 | WBS005 | A1120 | Plumbing First Fix | Task | 22 | 0 | 100 | Complete | 23-Jul-2026 | 14-Aug-2026 | 2026-07-23 | 2026-08-14 | 2026-07-26 | 2026-08-17 | 3 | N
A1130 | WBS005 | A1130 | HVAC Ductwork Installation | Task | 20 | 20 | 0 | Not Started |  |  | 2026-08-17 | 2026-09-06 | 2026-08-17 | 2026-09-06 | 0 | Y
A1140 | WBS005 | A1140 | MEP Second Fix | Task | 20 | 20 | 0 | Not Started |  |  | 2026-10-14 | 2026-11-03 | 2026-10-14 | 2026-11-03 | 0 | Y
A1150 | WBS006 | A1150 | Blockwork & Partitions | Task | 20 | 20 | 0 | Not Started |  |  | 2026-09-06 | 2026-09-26 | 2026-09-06 | 2026-09-26 | 0 | Y
A1160 | WBS006 | A1160 | Plastering & Screeding | Task | 18 | 18 | 0 | Not Started |  |  | 2026-09-26 | 2026-10-14 | 2026-09-26 | 2026-10-14 | 0 | Y
A1170 | WBS006 | A1170 | Flooring & Tiling | Task | 20 | 20 | 0 | Not Started |  |  | 2026-10-14 | 2026-11-03 | 2026-10-14 | 2026-11-03 | 0 | Y
A1180 | WBS006 | A1180 | Painting & Decoration | Task | 15 | 15 | 0 | Not Started |  |  | 2026-11-03 | 2026-11-18 | 2026-11-03 | 2026-11-18 | 0 | Y
MS130 | WBS006 | MS130 | Finishes Complete | Milestone | 0 | 0 | 0 | Not Started |  |  | 2026-11-18 | 2026-11-18 | 2026-11-18 | 2026-11-18 | 0 | Y
A1190 | WBS007 | A1190 | External Landscaping | Task | 15 | 0 | 100 | Complete | 11-Jun-2026 | 26-Jun-2026 | 2026-06-11 | 2026-06-26 | 2026-11-18 | 2026-12-03 | 160 | N
A1200 | WBS007 | A1200 | Site Boundary Wall | Task | 12 | 0 | 100 | Complete | 11-Jun-2026 | 23-Jun-2026 | 2026-06-11 | 2026-06-23 | 2026-11-21 | 2026-12-03 | 163 | N
A1210 | WBS007 | A1210 | Testing & Commissioning | Task | 15 | 15 | 0 | Not Started |  |  | 2026-11-18 | 2026-12-03 | 2026-11-18 | 2026-12-03 | 0 | Y
MS140 | WBS007 | MS140 | Practical Completion / Handover | Milestone | 0 | 0 | 0 | Not Started |  |  | 2026-12-03 | 2026-12-03 | 2026-12-03 | 2026-12-03 | 0 | Y

## Relationships
Predecessor Activity ID | Successor Activity ID | Relationship Type | Lag (days)
MS100 | A1010 | FS | 0
A1010 | A1020 | FS | 0
A1020 | A1030 | FS | 0
A1030 | A1040 | FS | 0
A1040 | A1050 | FS | 0
A1050 | A1060 | FS | 0
A1060 | MS110 | FS | 0
MS110 | A1070 | FS | 0
A1070 | A1080 | FS | 0
A1080 | A1090 | FS | 0
A1090 | A1100 | FS | 0
A1100 | MS120 | FS | 0
MS120 | A1110 | FS | 3
MS120 | A1120 | FS | 3
A1110 | A1130 | FS | 0
A1120 | A1130 | FS | 0
A1130 | A1150 | FS | 0
A1150 | A1160 | FS | 0
A1160 | A1140 | FS | 0
A1160 | A1170 | FS | 0
A1140 | A1180 | FS | 0
A1170 | A1180 | FS | 0
A1180 | MS130 | FS | 0
MS110 | A1190 | FS | 30
MS110 | A1200 | FS | 30
MS130 | A1210 | FS | 0
A1190 | MS140 | FS | 0
A1200 | MS140 | FS | 0
A1210 | MS140 | FS | 0

## Resources
Resource ID | Resource Name | Resource Type | Unit of Measure | Cost per Unit (EGP)
R001 | Site Engineer | Labor | hr | 150
R002 | Skilled Labor - Civil | Labor | hr | 90
R003 | Skilled Labor - MEP | Labor | hr | 110
R004 | Tower Crane | Nonlabor | hr | 800
R005 | Concrete Pump | Nonlabor | hr | 650
R006 | Excavator | Nonlabor | hr | 500
R007 | Ready-Mix Concrete | Material | m3 | 2200
R008 | Reinforcement Steel | Material | ton | 45000
R009 | Formwork System | Material | m2 | 350

## Assignments
Activity ID | Resource ID | Budgeted Units | Actual Units | Budgeted Cost (EGP) | Actual Cost (EGP)
A1010 | R001 | 80 | 84.8 | 12000 | 12720
A1020 | R001 | 56 | 50.8 | 8400 | 7620
A1030 | R006 | 160 | 155 | 80000 | 77500
A1030 | R002 | 320 | 305.9 | 28800 | 27531
A1040 | R002 | 500 | 542.1 | 45000 | 48789
A1040 | R004 | 200 | 213.8 | 160000 | 171040
A1050 | R002 | 360 | 404.3 | 32400 | 36387
A1050 | R007 | 450 | 414.8 | 990000 | 912560
A1050 | R008 | 60 | 60.3 | 2700000 | 2713500
A1060 | R002 | 400 | 363 | 36000 | 32670
A1060 | R007 | 380 | 362.8 | 836000 | 798160
A1070 | R002 | 360 | 369.5 | 32400 | 33255
A1070 | R004 | 144 | 130.6 | 115200 | 104480
A1070 | R007 | 420 | 398.9 | 924000 | 877580
A1070 | R008 | 55 | 58.4 | 2475000 | 2628000
A1080 | R002 | 360 | 373 | 32400 | 33570
A1080 | R004 | 144 | 137.5 | 115200 | 110000
A1080 | R007 | 420 | 439.9 | 924000 | 967780
A1080 | R008 | 55 | 60.6 | 2475000 | 2727000
A1090 | R002 | 360 | 324.6 | 32400 | 29214
A1090 | R004 | 144 | 158.6 | 115200 | 126880
A1090 | R007 | 420 | 451.3 | 924000 | 992860
A1090 | R008 | 55 | 54.2 | 2475000 | 2439000
A1100 | R002 | 300 | 281.7 | 27000 | 25353
A1100 | R004 | 120 | 136.7 | 96000 | 109360
A1100 | R007 | 350 | 344.5 | 770000 | 757900
A1100 | R008 | 45 | 41.5 | 2025000 | 1867500
A1110 | R003 | 500 | 443.6 | 55000 | 48796
A1120 | R003 | 440 | 489.2 | 48400 | 53812
A1130 | R003 | 400 | 0 | 44000 | 0
A1140 | R003 | 400 | 0 | 44000 | 0
A1150 | R002 | 400 | 0 | 36000 | 0
A1150 | R009 | 180 | 0 | 63000 | 0
A1160 | R002 | 360 | 0 | 32400 | 0
A1170 | R002 | 400 | 0 | 36000 | 0
A1180 | R002 | 300 | 0 | 27000 | 0
A1190 | R002 | 200 | 210.2 | 18000 | 18918
A1200 | R002 | 200 | 220.4 | 18000 | 19836
A1200 | R007 | 80 | 86.6 | 176000 | 190520
A1210 | R001 | 120 | 0 | 18000 | 0
A1210 | R003 | 200 | 0 | 22000 | 0